## 1. Backlog
15C - 15 CASTAWAY
Internal Use
Featrues |  | Valor
menu
suporte a um número variável de fases
tabuleiro de tamanho variável
peças com comportamentos peculiares
cursor customizado (versão flash)
game over/rollback
stage clear
victory
reset game
contador de movimentos* mostrado em tela
next stage
previous stage
highscores
how to play
suporte a sons - mute
suporte a música - mute
pause on focus out

## 2. Project Dashboard
15C - 15 CASTAWAY
Internal Use
Product burndown and metrics
| Sprint | SP | SPR | %SP | %Var(h) | BV | BVR | %BV | End Sprint | Sprint | Test | Passed | Failed | Notes
| S01 | [8 empty] | S01
| S02 | [8 empty] | S02
| S03 | [8 empty] | S03
| S04 | [8 empty] | S04
| Remain | [8 empty] | Remain
| TOTALS | [8 empty] | TOTALS | 0 | 0 | 0
Sprint progress - Updated on | [5 empty] | 2010-09-13
Sprint Current (01)
Estimates (h)
| Planned | Worked | EETC | %Var
| 33.5 | 0.32468 | 0 | -99.03%
Story Points
| Planned | Final |  | %Var
Progress
Sprint 01 - Objective
Sprint 01 - Feedback
<Please provide your opinion about this sprint deliverable by sending us an e-mail.>

## 3. Resources
15C - 15 CASTAWAY
Uso Interno
Resources
Team Performance
2010-09-13
[12 empty] | Days left | Hours Left
[12 empty] | 10 | 26
Daily Productivity Goal (h)
2.6
Team daily productivity average (h)
12.5
Chances to Complete (%)
Impact on Progress | [11 empty] | 100%
Team efficiency over 75%
92%
Team efficiency over 100%
78%
Team Progress and Efficiency
Sprint burndown
10 | Planned | 2010-09-11 | 2010-09-12 | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24
|  | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
Day | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1
Story Points (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | 33.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5
Remaining (h) | 33.5 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Productive hours (Time Sheet) | 0 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative Hours (Actual hours) | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5
New Tasks (hours) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target daily hours | 0 | 3.35 | 2.6 | 2.6 | 2.8889 | 3.25 | 3.7143 | 4.3333 | 5.2 | 5.2 | 5.2 | 6.5 | 8.6667 | 13 | 26
Daily missed hours | 0 | 9.15 | -2.6 | -2.6 | -2.8889 | -3.25 | -3.7143 | -4.3333 | -5.2 | -5.2 | -5.2 | -6.5 | -8.6667 | -13 | -26
Daily productive hours (AVG) |  | 12.5 | 12.5 | 12.5 | 6.25 | 4.17 | 3.13 | 2.5 | 2.08 | 2.08 | 2.08 | 1.79 | 1.56 | 1.39 | 1.25
Chances to Complete (%) | 100% | 100% | 100% | 100% | 100% | 100% | 84% | 58% | 40% | 40% | 40% | 28% | 18% | 11% | 5%
Team efficiency over (75%) | 100% | 0% | 0% | 92% | 46% | 31% | 23% | 18% | 0% | 0% | 15% | 13% | 11% | 10% | 9%
Team efficiency over (100%) | 100% | 0% | 0% | 78% | 39% | 26% | 20% | 16% | 0% | 0% | 13% | 11% | 10% | 9% | 8%
Projection based on total hours avaiable using 75% productivity target
Target daily hours | 13.6 | 0 | 0 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 0 | 0 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6
Secured limit | 136 | 136 | 136 | 122.4 | 108.8 | 95.2 | 81.6 | 68 | 68 | 68 | 54.4 | 40.8 | 27.2 | 13.6 | 2.4869e-14
Projection based on total ideal hours avaiable using 100% productivity target
Target daily hours | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16
Risk limit | 160 | 160 | 160 | 144 | 128 | 112 | 96 | 80 | 80 | 80 | 64 | 48 | 32 | 16 | 0
Impediments
Day |  | 2010-09-11 | 2010-09-12 | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24
New
Closed
Impediments
Team planned hours | bar: 2010-09-11 to 2010-09-19
Resource name | Type | Ideal Hours | % Prod | Hrs disp | Days | Total Prod (h) | Total Ideal (h) | Actual(h) | % Var 85% | % Var 100%
Cesar | PRG | 4 | 85% | 3.4 | 10 | 34 | 40 | 0 | 0% | 0%
Caio - Áudio | AUD | 4 | 85% | 3.4 | 10 | 34 | 40 | 1.5 | 4.412% | 3.75%
Caio - Arte | ART | 4 | 85% | 3.4 | 10 | 34 | 40 | 8.5 | 25% | 21.25%
Caio - Design | GD | 4 | 85% | 3.4 | 10 | 34 | 40 | 2.5 | 7.353% | 6.25%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 12.5 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
|  | 0 | 85% | 0 | 10 | 0 | 0 | 0 | 0% | 0%
TOTAL |  | 2010-09-11: 16; 2010-09-13: 13.6; 2010-09-15: 136; 2010-09-16: 160; 2010-09-17: 12.5; 2010-09-18: 9.191%; 2010-09-19: 7.812%
Resource Status | bar: 2010-09-11 to 2010-09-18
Resource name | Worked Days | 2010-09-11: EETC; 2010-09-12: Work; 2010-09-13: Percent done; 2010-09-14: Productivity (h/day); 2010-09-15: Productivity Percent; 2010-09-16: Ideal Productivity Percent; 2010-09-17: Produtivity Target (h/day); 2010-09-18: Impediments
Cesar | 1 | 2010-09-11: 18; 2010-09-12: 0; 2010-09-13: 0%; 2010-09-14: 0; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 2; 2010-09-18: 0
Caio - Áudio | 1 | 2010-09-11: 0; 2010-09-12: 1.5; 2010-09-13: 100%; 2010-09-14: 1.5; 2010-09-15: 44.12%; 2010-09-16: 37.5%; 2010-09-17: 0; 2010-09-18: 0
Caio - Arte | 1 | 2010-09-11: 0; 2010-09-12: 8.5; 2010-09-13: 100%; 2010-09-14: 8.5; 2010-09-15: 250%; 2010-09-16: 212.5%; 2010-09-17: 0; 2010-09-18: 0
Caio - Design | 1 | 2010-09-11: 8; 2010-09-12: 2.5; 2010-09-13: 23.81%; 2010-09-14: 2.5; 2010-09-15: 73.53%; 2010-09-16: 62.5%; 2010-09-17: 0.88889; 2010-09-18: 0
0 | 1 | 2010-09-11: 0; 2010-09-12: 0; 2010-09-13: 100%; 2010-09-14: 0; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 0; 2010-09-18: 0
0 | 1 | 2010-09-11: 0; 2010-09-12: 0; 2010-09-13: 100%; 2010-09-14: 0; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 0; 2010-09-18: 0
0 | 1 | 2010-09-11: 0; 2010-09-12: 12.5; 2010-09-13: 100%; 2010-09-14: 12.5; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 0; 2010-09-18: 0
0 | 1 | 2010-09-11: 0; 2010-09-12: 0; 2010-09-13: 100%; 2010-09-14: 0; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 0; 2010-09-18: 0
0 | 1 | 2010-09-11: 0; 2010-09-12: 0; 2010-09-13: 100%; 2010-09-14: 0; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 0; 2010-09-18: 0
0 | 1 | 2010-09-11: 0; 2010-09-12: 0; 2010-09-13: 100%; 2010-09-14: 0; 2010-09-15: 0%; 2010-09-16: 0%; 2010-09-17: 0; 2010-09-18: 0
TEAM | 1 | 2010-09-11: 26; 2010-09-12: 12.5; 2010-09-13: 32.47%; 2010-09-14: 12.5; 2010-09-15: 91.91%; 2010-09-16: 78.12%; 2010-09-17: 2.8889; 2010-09-18: 0
Daily Report (scrum task + my tasks) from Target Process
Resource name | Total | 2010-09-11 | 2010-09-12 | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24
Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Caio - Áudio | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Caio - Arte | 8.5 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Caio - Design | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impediments | bar: 2010-09-11 to 2010-09-18
Description |  | 2010-09-11: IBL; 2010-09-14: Found Date; 2010-09-15: Closed Date; 2010-09-16: Solution

## 4. Timesheet
15C - 15 CASTAWAY
Uso Interno
Timesheet
Sprint Backlog Items
IBL Name | Baseline [h] | Actual [h] | Done [h] | Resource name |  | Type | Compl [%] | Report | [13 empty] | Remaining [h] | Story Points | Var [%] | Var [h]
[8 empty] | 2010-09-11 | 2010-09-12 | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24
[8 empty] | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
Sprint Backlog | 33.5 | 38.5 | 12.5 |  |  |  | 32.47% | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 |  | 14.93% | 5
FEATURE 01
portar código | 6 | 6 | 0 | Cesar |  | PRG | 0% | [14 empty] | 6 |  | 0% | 0
condições de vitória | 6 | 6 | 0 | Cesar |  | PRG | 0% | [14 empty] | 6 |  | 0% | 0
suporte a resolução variável de tela | 6 | 6 | 0 | Cesar |  | PRG | 0% | [14 empty] | 6 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 02
rollback | 1 | 1 | 1 | Caio - Arte |  | ART | 100% | [14 empty] | 0 |  | 0% | 0 | bar: 2010-09-11
dead shark | 1 | 1 | 1 | Caio - Arte |  | ART | 100% | [14 empty] | 0 |  | 0% | 0 | bar: 2010-09-11
barcos | 1 | 1 | 1 | Caio - Arte |  | ART | 100% | [14 empty] | 0 |  | 0% | 0 | bar: 2010-09-11
náufragos | 1 | 2 | 2 | Caio - Arte |  | ART | 100% | 2010-09-11: 2 | 0 |  | 100% | -1
background | 0.5 | 0.5 | 0.5 | Caio - Arte |  | ART | 100% | 2010-09-11: 0.5 | 0 |  | 0% | 0
tela de level start | 1 | 3 | 3 | Caio - Arte |  | ART | 100% | 2010-09-11: 3 | 0 |  | 200% | -2
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 03
- 2 normais - easy | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 normais - dificuldade média | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 normais - hard | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 em qualquer dificuldade com barco unidirecional | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 em qualquer dificuldade com barco multidirecional | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 em qualquer dificuldade com criança | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 em qualquer dificuldade com minas que matam | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
- 2 em qualquer dificuldade com minas que afastam | 1 | 1 | 0 | Caio - Design |  | GD | 0% | [14 empty] | 1 |  | 0% | 0
Atualizar documentação | 2 | 2.5 | 2.5 | Caio - Design |  | GD | 100% | 2010-09-11: 2.5 | 0 |  | 25% | -0.5
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 04
Sounds | 0 | 1.5 | 1.5 | Caio - Áudio |  | AUD | 100% | 2010-09-11: 1.5 | 0 |  | 0% | -1.5
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 05
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
FEATURE 06
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
|  |  | 0 | Resource name |  |  | 0% | [14 empty] | 0 |  | 0% | 0
Impediments
[8 empty] | Description |  |  |  | IBL |  |  |  | Found Date |  | Closed Date |  | Solution

## 5. Burndown Task Tables
15C - 15 CASTAWAY
Uso Interno
Burndown Task Tables
Task Type Burndown
10 |  | Planned | 2010-09-11 | 2010-09-12 | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24
|  |  | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
Day |  | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1
Actual (h) | TOT | 33.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5
Actual (h) | GD | 10 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5
Actual (h) | ART | 5.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5
Actual (h) | PRG | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Actual (h) | AUD | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Actual (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | TOT | 0 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | GD | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | ART | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | PRG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | AUD | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | TOT | 0 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5
Cumulative (h) | GD | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Cumulative (h) | ART | 0 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5
Cumulative (h) | PRG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | AUD | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Cumulative (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | TOT | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | GD | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | ART | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | PRG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | AUD | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | TOT | 33.5 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Remaining (h) | GD | 10 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Remaining (h) | ART | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | PRG | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Remaining (h) | AUD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total hours avaiable using 75% productivity target
Target Daily (h) | TOT | 13.6 | 0 | 0 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 0 | 0 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6
Target Daily (h) | GD | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4
Target Daily (h) | ART | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4
Target Daily (h) | PRG | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4
Target Daily (h) | AUD | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4 | 0 | 0 | 3.4 | 3.4 | 3.4 | 3.4 | 3.4
Target Daily (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | TOT | 136 | 136 | 136 | 122.4 | 108.8 | 95.2 | 81.6 | 68 | 68 | 68 | 54.4 | 40.8 | 27.2 | 13.6 | 2.4869e-14
Secured Limit | GD | 34 | 34 | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 17 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15
Secured Limit | ART | 34 | 34 | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 17 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15
Secured Limit | PRG | 34 | 34 | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 17 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15
Secured Limit | AUD | 34 | 34 | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 17 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15
Secured Limit | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total ideal hours avaiable using 100% productivity target
Target Daily (h) | TOT | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 16 | 16 | 16 | 16
Target Daily (h) | GD | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4
Target Daily (h) | ART | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4
Target Daily (h) | PRG | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4
Target Daily (h) | AUD | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 4 | 4 | 4
Target Daily (h) | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | TOT | 160 | 160 | 160 | 144 | 128 | 112 | 96 | 80 | 80 | 80 | 64 | 48 | 32 | 16 | 0
Risk Limit | GD | 40 | 40 | 40 | 36 | 32 | 28 | 24 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0
Risk Limit | ART | 40 | 40 | 40 | 36 | 32 | 28 | 24 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0
Risk Limit | PRG | 40 | 40 | 40 | 36 | 32 | 28 | 24 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0
Risk Limit | AUD | 40 | 40 | 40 | 36 | 32 | 28 | 24 | 20 | 20 | 20 | 16 | 12 | 8 | 4 | 0
Risk Limit | TST | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 6. Burndown Task Graphs
15C - 15 CASTAWAY
Uso Interno
Burndown Task Graphics

## 7. Burndown Resources Tables
15C - 15 CASTAWAY
Uso Interno
Burndown Resource Tables
Task Type Burndown
10 |  | Planned | 2010-09-11 | 2010-09-12 | 2010-09-13 | 2010-09-14 | 2010-09-15 | 2010-09-16 | 2010-09-17 | 2010-09-18 | 2010-09-19 | 2010-09-20 | 2010-09-21 | 2010-09-22 | 2010-09-23 | 2010-09-24
|  |  | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05
Day |  | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 1
Actual (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Productive (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Tasks (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total hours avaiable using 75% productivity target
Target Daily (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Secured Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projection based on total ideal hours avaiable using 100% productivity target
Target Daily (h) | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target Daily (h) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | TOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Cesar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Caio - Áudio | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Caio - Arte | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | Caio - Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Risk Limit | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## CONFIG
HR Type
GD
ART
PRG
AUD
TST